## Sheet1
LOCATE PLATE ISSUE SHEET
Sr No | Date | Browser | Bug Summary | Screenshot | Page name | Priority | Assigned to | Assigned by | Status | Resolved/ Solved
1 | 2021-04-05 | Chrome | After clicking on Register button it's not proceed further | Screeshot\admin.png | On register page | HIgh | sanjay | Pooja | new | working fine
2 | 2021-04-06 | Chrome | Restautant>Edit>Only image file should be accept currenttly text file is accepted | Screeshot\image.png | https://staging.locateplate.com/Admin/Restaurant/Edit/44 | HIgh | sanjay | Pooja | new | not solved
3 | 2021-04-06 | Chrome | On required field atsterisk should be show | Screeshot\required field.png | https://staging.locateplate.com/Admin/Restaurant/Edit/44 | medium | sanjay | Pooja | new | not solved
4 | 2021-04-06 | Chrome | Restautant>Edit>while entering data tap the enter key than details updated which should be not happen. |  | https://staging.locateplate.com/Admin/Restaurant/Edit/44 | medium | sanjay | Pooja | new | Type and press tab button>that's the issue
5 | 2021-04-06 | Chrome | After updating or deleting the details pop up should be show.(if details updated or deleted successfully then successfully popup message if not than not updated or deleted message should be show) |  | https://staging.locateplate.com/Admin/Restaurant/Edit/44 | medium | sanjay | Pooja | new | will check it later after delete but starts working
6 | 2021-04-06 | Chrome | select Restaurant from side menu try to delete the restaurant but not deleted |  | https://staging.locateplate.com/Admin/Restaurant/Edit/44 | medium | sanjay | Pooja | new | not solved
7 | 2021-04-06 | Chrome | On restaurant page when select the restaurant from the drop down than selected restaurant should be show | Screeshot\restaurant_dropdown.png | https://staging.locateplate.com/Admin/Restaurant/Edit/44 | medium | sanjay | Pooja | new | not solved
8 | 2021-04-06 | Chrome | When click on lunch dinner and breakfast then error showing |  |  | High | sanjay | Pooja | new
9 | 2021-04-07 | Chrome | when number of guest and time is not selected then click on the "Book" then pop up message should be show like please select number of guest or time |  | https://staging.locateplate.com/brampton/restaurants | High | sanjay | Pooja | new
10 | 2021-04-07 | Chrome | While creating restaurant if image is not uploaded then by default image should be show | Screeshot\order.png | https://staging.locateplate.com/Brampton/restaurant/montanas-9065-airport-rd,-brampton | medium | sanjay | Pooja | new
11 | 2021-04-07 | Chrome | Restaurant menu Images get corrupted, when try to edit the menu |  | https://staging.locateplate.com/brampton/restaurants | medium | sanjay | Pooja | new
12 | 2021-04-07 | Chrome | Sliders for more than one images uploaded to restaurant main page |  |  | medium | sanjay | Pooja | new
13 | 2021-04-07 | Chrome | Menu>edit details>on image part close button should be there to remove that image |  |  | low | sanjay | Pooja | new
14 | 2021-04-07 | Chrome | Menu>Edit> when change the any details from menu item. then uploaded image is removed |  |  | High | sanjay | Pooja | new
15 | 2021-04-07 | Chrome | When user book the table than that entry should be show in the all orders tab |  |  | High | sanjay | Pooja | new

## resolved
LOCATE PLATE ISSUE SHEET
Sr. No | Date | Browser | Bug Summary | Screenshot | Page name | Priority | Assigned to | Assigned by | Status | Resolved/ Solved